# Midterm Progress Report

Table of Contents

Team Members	1

Project Topic	1

Given Requirements	1

Implementation	2

Timeline	2

Milestones	2

Task Level Progress	3

Challenges & Outcomes	3

Timeline Catchup & Mitigation	3

Output	4

# Team Members

| Sr No. | Name |
| --- | --- |
| 1 | Kayvan Shah |

# Project Topic

| Title | FireMongo |
| --- | --- |
| Name | Firebase Emulator |
| About | Firebase Realtime Database RESTful API Emulation |

# Given Requirements

Requirements on your prototype system (database server):

- RESTful API which supports functions in Firebase RESTful API, which include: PUT, GET, POST, PATCH, DELETE, and filtering functions: orderBy=”$key”/”$value”/”name”, limitToFirst/Last, equalTo, startAt/endAt.

- Store JSON data in another database

- It should have a proper index created in the database to support orderBy. For example, for orderBy=”name” on users.json, it should create an index on the name.

- A command-line interface that allows users to query/update the content of the database using the curl command (similar to that in Firebase), for example:

  - curl -X GET 'http://localhost:5000/users.json?orderBy="name"&limitToFirst=5'

  - curl -X PUT 'http://localhost:5000/users/200.json' -d '{"name": "john", "age": 25}'

- Note: the command should return data/response in JSON format like that in Firebase

# Implementation

## Timeline

| Week | Dates | Tasks |
| --- | --- | --- |
| Week 1 | Feb 13-Feb 19 | - Finalizing the tech stack - Going through the tutorials - Design API - Creating a Git Repo & project’s directory structure - Sample data |
| Week 2 | Feb 20-Feb 26 | - Data modeling - PUT request function - POST request function |
| Week 3 | Feb 27-Mar 5 | - GET request function and filters |
| Week 4 | Mar 6-Mar 12 | - PATCH request function - DELETE request function |
| Week 5 | Mar 13-Mar 19 | - Deployment on a free site hosting platform OR using Docker - Test using “curl” |
| Week 6 | Mar 20-Mar 26 | Midterm Progress Report TESTING + BUG FIXES Documentation – Docstrings, Readme & Setup |
| Week 7 | Mar 27-Apr 2 | TESTING Video Documentation |
| Week 8 | Apr 3-Apr 9 | Final Report |
| Week 9 | Apr 10-Apr 16 | BUFFER TIME |
| Week 10 | Apr 17-Apr 23 | BUFFER TIME |

## Milestones

| NAME | STATUS |
| --- | --- |
| Finalizing the tech stack | COMPLETED |
| API DESIGN | COMPLETED |
| DATA MODELING - V1 - V2 | IN PROGRESS COMPLETED IN PROGRESS |
| REPOSITORY DIRECTORY STRUCTURE | COMPLETED |
| ENDPOINTS - V1 - V2 | IN PROGRESS COMPLETED IN PROGRESS |
| TEST CURL COMMANDS | TODO |
| LANDING PAGE | COMPLETED |
| DEPLOYMENT | TODO |
| DOCUMENTATIONs | TODO |

## Task Level Progress

Some milestones are tasks by themselves, so they are not repeated below.

| NAME | STATUS |
| --- | --- |
| ENDPOINTS version 1 - post - put - patch - delete - get | DEPRECATED COMPLETED COMPLETED COMPLETED COMPLETED BLOCKED |
| ENDPOINTS version 2 - post - put - patch - delete - get | IN PROGESS IN PROGESS IN PROGESS IN PROGESS IN PROGESS TODO |
| documentation - DOCstrings - API DOCS | IN PROGRESS IN PROGRESS TODO |
| deployment - DOCKER - hosting | TODO |
| testing - CURL - deployment | TODO |

## Challenges & Outcomes

- Data model used in version 1 of endpoints didn’t turn out to be feasible when retrieving data from the client end.

  - Followed a nested document structure, where every document in a collection had its schema.

  - Used a single collection for housing all the incoming data.

  - Create, Update & Delete operations were simplified using this data model.

  - Read operation turned out to be complicated, which involved writing complex queries on the database server side and writing complex filter logic to get the desired results.

  - The retrieval approach failed for basic filters and hence deprecated it.

## Timeline Catchup & Mitigation

- Unexpected challenges pushed some important & secondary tasks to the upcoming week nearing the deadline and stressing the workload. Hopefully, a buffer time estimate becomes helpful here.

- Implement the ideas for a new data model such that indexing and querying data is easier by utilizing the prowess of the multiple Mongo Collections housing documents following similar JSON schema.

# Output

Link to Private GitHub Repository: https://github.com/KayvanShah1/firebase-realtime-db-emulator